## Cover
TEST REPORT DOCUMENT
Project Name | SEP490 Capstone Backend |  |  | Creator | QA Team
Project Code | SEP490_BE |  |  | Issue Date | 2026-04-20
Document Code | SEP490_BE_TestReport_v1.3 |  |  | Version | v1.3
Record of change
Effective Date | Version | Change Item | *A,D,M | Change description | Reference
2026-04-20 | v1.3 | Checkpoint-based rewrite | M | Converted report to checkpoint-driven validation with change-to-test traceability | Session checkpoints 038-047 + deployment verification logs
Note on D10: *A: Add M: Modify D: Delete

## Test Cases
TEST CASE LIST
Project Name |  | SEP490 Capstone Backend
Project Code |  | SEP490_BE
Test Environment Setup Description |  | Azure Container Apps, SQL Server, Redis, RabbitMQ, API Gateway, PayOS, Cloudinary, JWT test accounts.
No | Function Name | Sheet Name | Description | Pre-Condition
1 | Checkpoint 047 - Search, Deploy, Diagram Expansion | Feature1 | Added portfolio/community search, deployed services, completed architecture diagram artifacts | Checkpoint artifact exists; deployed services/log evidence; expected status: Passed
2 | Checkpoint 046 - Report Alerts Immediate-First | Feature1 | Changed notification aggregation to immediate-first delivery for report events | Checkpoint artifact exists; deployed services/log evidence; expected status: Passed
3 | Checkpoint 045 - Community Moderation E2E Rollout | Feature1 | Implemented report review outcomes and post visibility behavior after moderation | Checkpoint artifact exists; deployed services/log evidence; expected status: Passed
4 | Checkpoint 044 - PayOS Fixes and Follow Categories | Feature1 | Added follow category management and fixed PayOS-related payment handling paths | Checkpoint artifact exists; deployed services/log evidence; expected status: Passed
5 | Checkpoint 043 - PayOS Webhook Recovery Sprint | Feature1 | Hardened webhook verification and recovery handling for paid orders | Checkpoint artifact exists; deployed services/log evidence; expected status: Passed
6 | Checkpoint 042 - Payment Fix and Follows Deploy | Feature2 | Deployed payment/follow fixes and verified production revisions | Checkpoint artifact exists; deployed services/log evidence; expected status: Passed
7 | Checkpoint 041 - PayOS Webhook and AI Rollout | Feature2 | Rolled out webhook handling improvements and AI-related service integration points | Checkpoint artifact exists; deployed services/log evidence; expected status: Pending
8 | Checkpoint 040 - Payment Flow Hardening + AI Plan | Feature2 | Applied payment flow hardening and integration guardrails | Checkpoint artifact exists; deployed services/log evidence; expected status: Passed
9 | Checkpoint 039 - Subscription Admin API Fixes | Feature2 | Fixed admin subscription APIs and aligned status/reporting behavior | Checkpoint artifact exists; deployed services/log evidence; expected status: Passed
10 | Checkpoint 038 - Reviewers Complete, Application Fix Planned | Feature2 | Completed reviewer-side flow and prepared/validated application fix direction | Checkpoint artifact exists; deployed services/log evidence; expected status: Pending
12 | Authentication & Profile | Feature3 | Auth login/refresh + company/employee profile APIs | Auth + profile services deployed and reachable
13 | Moderation, Notification & Realtime | Feature4 | Report review, notification delivery/aggregation, realtime push | Admin/mod/user tokens and event pipeline available
14 | Deployment & Contract Verification | Feature5 | CORS/gateway, API contract checks, deployment/artifact integrity | Latest revisions and repository artifacts available

## Test Statistics
TEST STATISTICS
Project Name | SEP490 Capstone Backend |  | QA Team
Project Code | SEP490_BE |  | Reviewer/Approver
Document Code | SEP490_BE_TestReport_v1.3 |  | Issue Date |  |  | 2026-04-20
Notes | Checkpoint-based traceability report (CP038-CP047): each checkpoint mapped to explicit verification cases.
No | Module code | Passed | Failed | Pending | N/A | Number of test cases
1 | CP047-CP043 | 8 | 0 | 0 | 0 | 8
2 | CP042-CP038 | 3 | 0 | 2 | 0 | 5
3 | Feature3-AuthProfile | 6 | 0 | 2 | 0 | 8
4 | Feature4-ModNotifyRealtime | 5 | 0 | 3 | 0 | 8
5 | Feature5-DeployContract | 400% | 0% | 400% | 0% | 800%
| Test coverage |  | 84.62 | %
| Sub total | 26 | 0 | 11 | 0 | 37
| Test coverage |  | 70.27 | %
| Test successful coverage |  | 70.27 | %

## Feature 1
Feature | Checkpoint Validation - Product Features (CP047-CP043) | [13 empty] | Passed
Test requirement | Validate each checkpoint by tracing implemented changes to concrete API/system tests and observed outcomes. | [13 empty] | Failed
Number of TCs | 8 | [13 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1 | 8 | 0 | 0 | 0
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Feature A
CP-047-01 | CP047: Portfolio search by q + blockType | 1. GET /api/portfolio?q=react&blockType=SKILL 2. GET with invalid blockType | Valid type returns filtered list; invalid type returns 400. | Portfolio search code and deployment from CP047 available. | Passed | 2026-04-20 | QA Team | Pending |  |  | Pending
CP-047-02 | CP047: Community feed search | GET /api/community/posts?q=keyword | Feed filtered by description contains keyword (case-insensitive). | Community service CP047 revision deployed. | Passed | 2026-04-20 | QA Team | Pending |  |  | Pending
CP-046-01 | CP046: Immediate-first report notification | Create first report event and observe recipient notification timeline. | First report triggers immediate notification without waiting for aggregation window. | Notification service with CP046 logic active. | Passed | 2026-04-20 | QA Team | Pending |  |  | Pending
CP-045-01 | CP045: Moderation approve_violation behavior | 1. Report a post 2. Admin review action=approve_violation 3. Check feed and owner notification | Post removed from feed; owner receives moderation notification. | Admin/mod token and report endpoint available. | Passed | 2026-04-20 | QA Team
CP-045-02 | CP045: Moderation reject behavior | 1. Report a post 2. Admin review action=reject 3. Check feed and notifications | Post remains visible; no violation-removal notification sent. | Reject path enabled in moderation API. | Passed | 2026-04-20 | QA Team | Pending |  |  | Pending
CP-044-01 | CP044: Follow category create/assign constraints | 1. Create follow category 2. Assign category to follow 3. Attempt cross-company category usage | Create/assign succeeds for same company; cross-company assignment rejected. | Follow category migration and endpoints deployed. | Passed | 2026-04-20 | QA Team | Pending |  |  | Pending
CP-044-02 | CP044: Delete in-use category protection | DELETE category currently assigned to follow | Request blocked with business validation error. | Category is referenced by at least one follow. | Passed | 2026-04-20 | QA Team
CP-043-01 | CP043: PayOS webhook verification hardening | Send webhook payload variations (header/body signature combinations). | Valid body signature accepted; invalid signature rejected; source logging present. | Payment service CP043 revision active. | Passed | 2026-04-20 | QA Team | Pending |  |  | Pending
F1-09 | Community feed search by description | 1. GET /api/community/posts?q=keyword. | 200 OK; feed filters by description contains (case-insensitive). | At least one post contains keyword. | Passed | 2026-04-20 | QA Team
F1-10 | Community interaction chain: post -> comment -> save | 1. POST /api/community/posts. 2. POST /api/community/posts/{id}/comments. 3. POST /api/community/posts/{id}/save. | All operations succeed and relation data is queryable. | Two valid user tokens. | Passed | 2026-04-20 | QA Team
Recruitment
F1-11 | Create recruitment post with media | 1. POST /api/company-posts multipart payload. | 201 Created; post appears in feed/detail endpoints. | Recruiter token has companyId claim. | Passed | 2026-04-20 | QA Team
F1-12 | Review application request (status update) | 1. PUT /api/applications/{id}/status by recruiter owner. | 200 OK; status updated with business-rule enforcement. | Application belongs to recruiter company. | Pending
Note on E10: List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## Feature 2
Feature | Checkpoint Validation - Deployment & Integration (CP042-CP038) | [13 empty] | Passed
Test requirement | Validate deployment revisions, integration endpoints, and operational correctness per checkpoint. | [13 empty] | Failed
Number of TCs | 5 | [13 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1 | 3 | 0 | 2 | 0
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Feature B
CP-042-01 | CP042: Payment/follow production deployment revisions | Check container app latest revisions and health for payment/portfolio related services. | New revisions ready/running and serving API requests. | Azure CLI access to container app revision list. | Passed | 2026-04-20 | QA Team | Pending |  |  | Pending
CP-041-01 | CP041: PayOS + AI rollout integration smoke | Run smoke calls through rollout endpoints and observe service responses. | Endpoints respond successfully with expected contracts. | Rollout revisions available for target services. | Pending | 2026-04-20 | QA Team | Pending |  |  | Pending
CP-040-01 | CP040: Payment flow hardening regression | Replay core subscription->payment->webhook flow with hardened logic. | No signature bypass; expected transition sequence maintained. | Test order and webhook payload fixtures ready. | Passed | 2026-04-20 | QA Team | Pending |  |  | Pending
CP-039-01 | CP039: Subscription admin API fixes | Call updated admin subscription endpoints and verify statuses/results. | Endpoints return corrected data/state transitions per fix scope. | Admin credentials and sample subscriptions available. | Passed | 2026-04-20 | QA Team
CP-038-01 | CP038: Reviewer/application fix readiness verification | Check reviewer-complete path and application fix acceptance criteria items. | Reviewer flow stable; application fix items traceable and testable. | Checkpoint notes and implementation references available. | Pending |  |  | Pending |  |  | Pending
Payment, Notification, Operations | Send chat message after connection | 1. Login user A/B. 2. POST /api/connection/rooms/{roomId}/messages. | 201 Created; message persisted and realtime event emitted to room. | Room exists and caller belongs to room. | Pending |  |  | Pending |  |  | Pending
F2-05 | Create subscription checkout | 1. POST /api/subscriptions with planId. | 201 Created; pending subscription with paymentUrl/orderCode. | Active subscription plan exists. | Passed | 2026-04-20 | QA Team | Pending |  |  | Pending
F2-06 | Process payment webhook to success | 1. POST /api/payment/webhook with valid signature payload. | Payment transitions to Succeeded and outbox event stored. | Known valid signed webhook payload. | Pending
F2-07 | Create community report and trigger notification | 1. POST /api/community/posts/{id}/report. 2. Observe notification event path. | Notification aggregation flow targets admin/moderator recipients. | Reporter token valid and post exists. | Passed | 2026-04-20 | QA Team
F2-08 | Admin/moderator read report notifications | 1. Login admin/moderator. 2. Call notification list endpoint with access token. | 200 OK; report notification visible to authorized recipients. | At least one report generated. | Passed | 2026-04-20 | QA Team
F2-09 | Verify dashboard origin in service CORS | 1. Send preflight requests with Origin=https://sep-490-dashboard-fork.vercel.app. | Allowed origin is returned across updated services. | Services deployed with latest CORS config. | Passed | 2026-04-20 | QA Team
F2-10 | Verify API Gateway redeploy and routing | 1. Route requests via gateway to target services. | Gateway responds and forwards requests to active revisions. | api-gateway revision is running. | Passed | 2026-04-20 | QA Team
F2-11 | Verify portfolio preview contract uses id (not blockId) | 1. Call portfolio follow/preview related endpoint. | Response contains id field and omits blockId. | Portfolio with blocks exists. | Passed | 2026-04-20 | QA Team
F2-12 | Create interview schedule | 1. POST /api/interviews/schedules payload. | 201 Created; schedule persisted and candidate notified. | Recruiter role and valid candidate/application context. | Pending
Note on E10: List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## Feature 3
Feature | Authentication & Profile Management | [13 empty] | Passed
Test requirement | Validate auth token lifecycle and user profile management endpoints (company/employee). | [13 empty] | Failed
Number of TCs | 8 | [13 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1 | 6 | 0 | 2 | 0
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Feature C
F3-01 | Auth login returns access + refresh token | POST /api/Auth/login with valid credentials | 200 OK with accessToken and refreshToken. | Active user account exists. | Passed | 2026-04-20 | QA Team | Pending |  |  | Pending
F3-02 | Auth refresh token rotates successfully | POST /api/Auth/refresh with valid refresh token | 200 OK and new access token issued. | Existing non-revoked refresh token. | Passed | 2026-04-20 | QA Team | Pending |  |  | Pending
F3-03 | Create company profile with media | POST /api/Company multipart payload | 200 OK and company profile persisted. | Recruiter/user with eligible role and token. | Passed | 2026-04-20 | QA Team | Pending |  |  | Pending
F3-04 | Get company profile by user id | GET /api/company/by-user/{userId} | 200 OK with companyName/avatar/cover fields. | Company profile linked to user id. | Passed | 2026-04-20 | QA Team
F3-05 | Get employee profile by user id | GET /api/employee/by-user/{userId} | 200 OK with employee profile fields. | Employee profile linked to user id. | Passed | 2026-04-20 | QA Team | Pending |  |  | Pending
F3-06 | Unauthorized create profile blocked | Call profile create endpoint without token | 401 Unauthorized. | No Authorization header. | Passed | 2026-04-20 | QA Team | Pending |  |  | Pending
F3-07 | Role mismatch access blocked | Call restricted endpoint with wrong role token | 403 Forbidden. | Token valid but role not permitted. | Pending | 2026-04-20 | QA Team | Pending |  |  | Pending
F3-08 | Invalid login payload validation | POST /api/Auth/login with missing password | 400 validation error. | API model validation enabled. | Pending
F2-07 | Create community report and trigger notification | 1. POST /api/community/posts/{id}/report. 2. Observe notification event path. | Notification aggregation flow targets admin/moderator recipients. | Reporter token valid and post exists. | Passed | 2026-04-20 | QA Team
F2-08 | Admin/moderator read report notifications | 1. Login admin/moderator. 2. Call notification list endpoint with access token. | 200 OK; report notification visible to authorized recipients. | At least one report generated. | Passed | 2026-04-20 | QA Team
F2-09 | Verify dashboard origin in service CORS | 1. Send preflight requests with Origin=https://sep-490-dashboard-fork.vercel.app. | Allowed origin is returned across updated services. | Services deployed with latest CORS config. | Passed | 2026-04-20 | QA Team
F2-10 | Verify API Gateway redeploy and routing | 1. Route requests via gateway to target services. | Gateway responds and forwards requests to active revisions. | api-gateway revision is running. | Passed | 2026-04-20 | QA Team
F2-11 | Verify portfolio preview contract uses id (not blockId) | 1. Call portfolio follow/preview related endpoint. | Response contains id field and omits blockId. | Portfolio with blocks exists. | Passed | 2026-04-20 | QA Team
F2-12 | Create interview schedule | 1. POST /api/interviews/schedules payload. | 201 Created; schedule persisted and candidate notified. | Recruiter role and valid candidate/application context. | Pending
Note on E10: List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## Feature 4
Feature | Moderation, Notification & Realtime | [13 empty] | Passed
Test requirement | Validate report moderation, notification targeting/aggregation, and realtime delivery behaviors. | [13 empty] | Failed
Number of TCs | 8 | [13 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1 | 5 | 0 | 3 | 0
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Feature D
F4-01 | Create post report by user | POST /api/community/posts/{postId}/report | 201 Created with report record. | Reporter token and existing post. | Passed | 2026-04-20 | QA Team | Pending |  |  | Pending
F4-02 | Prevent duplicate report from same user | Repeat report request for same post by same user | 400 BadRequest duplicate error. | Existing pending report by same reporter. | Passed | 2026-04-20 | QA Team | Pending |  |  | Pending
F4-03 | Admin list reports | GET /api/community/admin/reports | 200 OK with paged report list. | Admin/moderator token. | Passed | 2026-04-20 | QA Team | Pending |  |  | Pending
F4-04 | Admin review report approve_violation | POST /api/community/admin/reports/{id}/review | Review saved; post hidden from public feed. | Pending report exists. | Passed | 2026-04-20 | QA Team
F4-05 | Admin review report reject | POST review action=reject | Report rejected; post remains visible. | Pending report exists. | Passed | 2026-04-20 | QA Team | Pending |  |  | Pending
F4-06 | Notification delivery to admin/mod for report | Create report then query notifications | Target roles receive report notification. | Notification service/realtime connected. | Pending |  |  | Pending |  |  | Pending
F4-07 | Notification aggregation in report window | Create multiple reports in window | Count aggregation behavior matches design. | Aggregation cache active. | Pending | 2026-04-20 | QA Team | Pending |  |  | Pending
F4-08 | Realtime consumer push to user group | Emit notification.created event | SignalR push to user_{id} group succeeds. | Realtime hub and consumer running. | Pending
F2-07 | Create community report and trigger notification | 1. POST /api/community/posts/{id}/report. 2. Observe notification event path. | Notification aggregation flow targets admin/moderator recipients. | Reporter token valid and post exists. | Passed | 2026-04-20 | QA Team
F2-08 | Admin/moderator read report notifications | 1. Login admin/moderator. 2. Call notification list endpoint with access token. | 200 OK; report notification visible to authorized recipients. | At least one report generated. | Passed | 2026-04-20 | QA Team
F2-09 | Verify dashboard origin in service CORS | 1. Send preflight requests with Origin=https://sep-490-dashboard-fork.vercel.app. | Allowed origin is returned across updated services. | Services deployed with latest CORS config. | Passed | 2026-04-20 | QA Team
F2-10 | Verify API Gateway redeploy and routing | 1. Route requests via gateway to target services. | Gateway responds and forwards requests to active revisions. | api-gateway revision is running. | Passed | 2026-04-20 | QA Team
F2-11 | Verify portfolio preview contract uses id (not blockId) | 1. Call portfolio follow/preview related endpoint. | Response contains id field and omits blockId. | Portfolio with blocks exists. | Passed | 2026-04-20 | QA Team
F2-12 | Create interview schedule | 1. POST /api/interviews/schedules payload. | 201 Created; schedule persisted and candidate notified. | Recruiter role and valid candidate/application context. | Pending
Note on E10: List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## Feature 5
Feature | Deployment, Contract & Artifact Verification | [13 empty] | Passed
Test requirement | Validate deployment outcomes, API contracts, CORS/gateway operations, and architecture artifact completeness. | [13 empty] | Failed
Number of TCs | 8 | [13 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1 | 4 | 0 | 4 | 0
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Feature E
F5-01 | CORS allows dashboard origin on services | Preflight from dashboard origin | Access-Control-Allow-Origin returned correctly. | Latest CORS config deployed. | Passed | 2026-04-20 | QA Team | Pending |  |  | Pending
F5-02 | API Gateway revision healthy after redeploy | Call gateway-routed endpoints | Gateway routes to backend services successfully. | api-gateway latest revision running. | Passed | 2026-04-20 | QA Team | Pending |  |  | Pending
F5-03 | Portfolio preview response contract | Call preview/follow-related endpoint | Response uses id and no blockId in preview contract. | Portfolio with blocks exists. | Passed | 2026-04-20 | QA Team | Pending |  |  | Pending
F5-04 | Payment webhook signature validation strictness | Send invalid signature payload | Webhook rejected; no success state update. | Webhook endpoint reachable. | Passed | 2026-04-20 | QA Team
F5-05 | Container app rollout verification matrix | Check updated service revisions | All targeted services show ready/running. | Azure permissions available. | Pending |  |  | Pending |  |  | Pending
F5-06 | Sequence diagrams completeness | Verify sequence_dia files | All expected diagram files exist and render Mermaid. | sequence_dia folder exists. | Pending |  |  | Pending |  |  | Pending
F5-07 | Package diagram completeness | Verify packagedia graph coverage | Major packages and dependencies are represented. | packagedia file exists. | Pending | 2026-04-20 | QA Team | Pending |  |  | Pending
F5-08 | Per-service class diagrams completeness | Verify class_dia files | All service-specific class diagrams present. | class_dia folder exists. | Pending
F2-07 | Create community report and trigger notification | 1. POST /api/community/posts/{id}/report. 2. Observe notification event path. | Notification aggregation flow targets admin/moderator recipients. | Reporter token valid and post exists. | Passed | 2026-04-20 | QA Team
F2-08 | Admin/moderator read report notifications | 1. Login admin/moderator. 2. Call notification list endpoint with access token. | 200 OK; report notification visible to authorized recipients. | At least one report generated. | Passed | 2026-04-20 | QA Team
F2-09 | Verify dashboard origin in service CORS | 1. Send preflight requests with Origin=https://sep-490-dashboard-fork.vercel.app. | Allowed origin is returned across updated services. | Services deployed with latest CORS config. | Passed | 2026-04-20 | QA Team
F2-10 | Verify API Gateway redeploy and routing | 1. Route requests via gateway to target services. | Gateway responds and forwards requests to active revisions. | api-gateway revision is running. | Passed | 2026-04-20 | QA Team
F2-11 | Verify portfolio preview contract uses id (not blockId) | 1. Call portfolio follow/preview related endpoint. | Response contains id field and omits blockId. | Portfolio with blocks exists. | Passed | 2026-04-20 | QA Team
F2-12 | Create interview schedule | 1. POST /api/interviews/schedules payload. | 201 Created; schedule persisted and candidate notified. | Recruiter role and valid candidate/application context. | Pending
Note on E10: List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case